## Project Planner
dont know yet
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Project Plan |  | 1 week |  |  | 0 | bar: PERIODS 3 to PERIODS 7
1.1 Project Overview |  | 1 days |  |  | 0% | bar: PERIODS 2
1.2 Work Breakdown Structure |  | 2 days |  |  | 0% | bar: PERIODS 2 to PERIODS 3; PERIODS 5; PERIODS 7
1.3 Activity Definition and Estimation |  | 2 days |  |  | 0% | bar: PERIODS 3 to PERIODS 5; PERIODS 7
1.4 Gantt Chart |  | 2 days |  |  | 0% | bar: PERIODS 3 to PERIODS 5; PERIODS 7
2. Software Design Document |  | 19 days |  |  | 0% | bar: PERIODS 3; PERIODS 5 to PERIODS 21
2.1 System Vision Statement |  | 6 hours |  |  | 0% | bar: PERIODS 5
2.1.1 Background |  | 2 hours |  |  | 0% | bar: PERIODS 5
2.1.2 Overview |  | 2 hours |  |  | 0% | bar: PERIODS 6
2.1.3 Benefits |  | 2 hours |  |  | 0% | bar: PERIODS 6
2.2 Requirements |  | 3 days |  |  | 0% | bar: PERIODS 6 to PERIODS 8
2.2.1 User Requirements |  | 1 day |  |  | 0% | bar: PERIODS 7
2.2.2 Software Requirements |  | 1 day |  |  | 0% | bar: PERIODS 8
2.2.3 Use Case Diagram |  | 4 hours |  |  | 0% | bar: PERIODS 9
2.2.4 Use Cases |  | 1 day |  |  | 0% | bar: PERIODS 10
2.3 Software Design and System Components |  | 10 days |  |  | 0% | bar: PERIODS 10 to PERIODS 19
2.3.1 Software Design |  | 1 day |  |  | 0% | bar: PERIODS 10
2.3.2 System Components |  | 9 days |  |  | 0% | bar: PERIODS 11 to PERIODS 19
2.3.2.1 Functions |  | 2 days |  |  | 0% | bar: PERIODS 11 to PERIODS 12
2.3.2.2 Data Structures |  | 2 days |  |  | 0% | bar: PERIODS 13 to PERIODS 14
2.3.2.3 Detailed design |  | 5 days |  |  | 0% | bar: PERIODS 15 to PERIODS 19
2.4 User Interface Design |  | 5 days |  |  | 0% | bar: PERIODS 20 to PERIODS 24
2.4.1 Structural Design |  | 1 day |  |  | 0% | bar: PERIODS 20
2.4.2 Visual Design |  | 4 days |  |  | 0% | bar: PERIODS 21 to PERIODS 24
3 Software Implementation |  | 13 days |  |  | 0% | bar: PERIODS 25 to PERIODS 37
3.1 Design Implementation |  | 3 days |  |  | 0% | bar: PERIODS 25 to PERIODS 27
3.1.1 UI Design |  | 3 days |  |  | 0% | bar: PERIODS 25 to PERIODS 27
3.2 Code Construction |  | 10 days |  |  | 0% | bar: PERIODS 28 to PERIODS 37
3.2.1 Landing Page Code |  | 4 days |  |  | 0% | bar: PERIODS 28 to PERIODS 31
3.2.2 Matplotlib Code |  | 3 days |  |  | 0% | bar: PERIODS 31 to PERIODS 33
3.2.3 Tkinter Code/wxPython |  | 3 days |  |  | 0% | bar: PERIODS 33 to PERIODS 35
3.2.4 Pandas Code |  | 3 days |  |  | 0% | bar: PERIODS 35 to PERIODS 37
4 Software Testing Report |  |  |  |  | 0% | bar: PERIODS 38 to PERIODS 48
4.1 Testing Plan |  | 5 days |  |  | 0% | bar: PERIODS 38 to PERIODS 42
4.2 Ongoing testing |  | ???? |  |  | 0%
4.3 User Manual |  | 7 days |  |  | 0% | bar: PERIODS 42 to PERIODS 48
5 Executive Summary |  |  |  |  | 0%
5.1 Analysis and Comments |  | 3 days |  |  | 0% | bar: PERIODS 49 to PERIODS 51
5.2 Git_log |  | 1hr |  |  | 0% | bar: PERIODS 52
0%
Project Completion |  |  |  |  | 0%
0%