## Project Planner
AJJ BNB
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION in Days | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Project Plan |  | 7 |  |  | 0 | bar: PERIODS 1 to PERIODS 7
1.1 Project Overview |  | 1 |  |  | 0% | bar: PERIODS 1 to PERIODS 21
1.2 Work Breakdown Structure |  | 2 |  |  | 0% | bar: PERIODS 1 to PERIODS 28
1.3 Activity Definition and Estimation |  | 2 |  |  | 0% | bar: PERIODS 2 to PERIODS 26
1.4 Gantt Chart |  | 2 |  |  | 0% | bar: PERIODS 3 to PERIODS 29
2. Software Design Document |  |  |  |  | 0% | bar: PERIODS 1 to PERIODS 12
2.1 System Vision Statement |  |  |  |  | 0% | bar: PERIODS 1
2.1.1 Background |  | 1 |  |  | 0% | bar: PERIODS 1 to PERIODS 27
2.1.2 Overview |  | 1 |  |  | 0% | bar: PERIODS 1 to PERIODS 24
2.1.3 Benefits |  | 1 |  |  | 0% | bar: PERIODS 1 to PERIODS 11
2.2 Requirements |  |  |  |  | 0% | bar: PERIODS 1 to PERIODS 4
2.2.1 User Requirements |  | 1 |  |  | 0% | bar: PERIODS 2
2.2.2 Software Requirements |  | 1 |  |  | 0% | bar: PERIODS 2
2.2.3 Use Case Diagram |  | 1 |  |  | 0% | bar: PERIODS 4
2.2.4 Use Cases |  | 1 |  |  | 0% | bar: PERIODS 3
2.3 Software Design and System Components |  |  |  |  | 0% | bar: PERIODS 3 to PERIODS 12
2.3.1 Software Design |  | 1 |  |  | 0% | bar: PERIODS 3
2.3.2 System Components |  |  |  |  | 0% | bar: PERIODS 4 to PERIODS 12
2.3.2.1 Functions |  | 4 |  |  | 0% | bar: PERIODS 4 to PERIODS 7
2.3.2.2 Data Structures |  | 2 |  |  | 0% | bar: PERIODS 8 to PERIODS 9
2.3.2.3 Detailed design |  | 3 |  |  | 0% | bar: PERIODS 10 to PERIODS 12
2.4 User Interface Design |  |  |  |  | 0% | bar: PERIODS 4 to PERIODS 6
2.4.1 Structural Design |  | 3 |  |  | 0% | bar: PERIODS 4 to PERIODS 6
2.4.2 Visual Design |  | 3 |  |  | 0% | bar: PERIODS 4 to PERIODS 6
3 Software Implementation |  |  |  |  | 0% | bar: PERIODS 13 to PERIODS 27
3.1 Design Implementation |  |  |  |  | 0% | bar: PERIODS 13 to PERIODS 19
3.1.1 Build the User Interface |  | 3 |  |  | 0% | bar: PERIODS 14 to PERIODS 15; PERIODS 29
3.1.2 Place the Buttons |  | 1 |  |  | 0% | bar: PERIODS 16; PERIODS 29
3.1.3 Add the Colours |  | 3 |  |  | 0% | bar: PERIODS 17 to PERIODS 19; PERIODS 29
3.1.4 Build the Layout |  | 5 |  |  | 0% | bar: PERIODS 14 to PERIODS 17; PERIODS 29
3.1.4 Build the Logo |  | 2 |  |  | 0% | bar: PERIODS 13 to PERIODS 14; PERIODS 29
3.2 Code Construction |  |  |  |  | 0% | bar: PERIODS 18 to PERIODS 26
3.2.1 Coding: Matplotlib |  | 3 |  |  | 0% | bar: PERIODS 18 to PERIODS 20
3.2.2 Coding: wxPython |  | 3 |  |  | 0% | bar: PERIODS 21 to PERIODS 23
3.2.3 Coding: Pandas |  | 3 |  |  | 0% | bar: PERIODS 24 to PERIODS 26
3.3 Design Integration |  |  |  |  | 0% | bar: PERIODS 22 to PERIODS 27
3.3.1 Coding: Landing Page |  | 1 |  |  | 0% | bar: PERIODS 22; PERIODS 30
3.3.2 Coding: Suburn Listing Page |  | 1 |  |  | 0% | bar: PERIODS 23
3.3.3 Coding: Price Chart Page |  | 1 |  |  | 0% | bar: PERIODS 24
3.3.4 Coding: Search Page |  | 1 |  |  | 0% | bar: PERIODS 25
3.3.5 Coding: Cleanliness Page |  | 1 |  |  | 0% | bar: PERIODS 26; PERIODS 31 to PERIODS 32
3.3.6 Coding: Display by Ratings Page |  | 1 |  |  | 0% | bar: PERIODS 27
4 Software Testing Report |  |  |  |  | 0% | bar: PERIODS 24 to PERIODS 31
4.1 Testing Plan |  |  |  |  | 0% | bar: PERIODS 24 to PERIODS 31
4.1.1 Document Test Cases |  | 5 |  |  | 0% | bar: PERIODS 24 to PERIODS 28
4.1.2 Build Test Data based on test Cases |  | 1 |  |  | 0% | bar: PERIODS 29
4.1.3 Perform user acceptance testing procedures |  | 2 |  |  | 0% | bar: PERIODS 29 to PERIODS 30
4.1.4 Write Reports of Test Results |  | 1 |  |  | 0% | bar: PERIODS 31
4.2 Build: User Manual |  | 1 |  |  | 0% | bar: PERIODS 32
5 Executive Summary |  |  |  |  | 0% | bar: PERIODS 2 to PERIODS 32
5.1 Analysis and Comments |  | 1 |  |  | 0% | bar: PERIODS 32
5.2 Git_log |  | 0.125 |  |  | 0%
0%
Project Completion |  |  |  |  | 0% | bar: PERIODS 1 to PERIODS 44