## Project Planner
AJJ BNB
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Project Plan |  | 1 week |  |  | 0 | bar: PERIODS 1 to PERIODS 7
1.1 Project Overview (develop project overview) |  | 1 day |  |  | 0% | bar: PERIODS 1
1.2 Work Breakdown Structure(formulate wbs) |  | 2 days |  |  | 0% | bar: PERIODS 1 to PERIODS 2; PERIODS 5; PERIODS 7
1.3 Activity Definition and Estimation(state activity) |  | 2 days |  |  | 0% | bar: PERIODS 1 to PERIODS 2; PERIODS 7
1.4 Gantt Chart(derive gantt chart from wbs) |  | 2 days |  |  | 0% | bar: PERIODS 2 to PERIODS 3; PERIODS 5; PERIODS 7
2. Software Design Document |  | 19 days? |  |  | 0% | bar: PERIODS 4 to PERIODS 22
2.1 System Vision Statement |  | 6 hours |  |  | 0% | bar: PERIODS 4
2.1.1 Background (explain the bckgrnd) |  | 2 hours |  |  | 0% | bar: PERIODS 4
2.1.2 Overview(give overview of doc) |  | 2 hours |  |  | 0% | bar: PERIODS 4
2.1.3 Benefits(Benefits of the Softwre) |  | 2 hours |  |  | 0% | bar: PERIODS 4
2.2 Requirements |  | 3 days |  |  | 0% | bar: PERIODS 4 to PERIODS 7
2.2.1 User Requirements(List user reqs) |  | 1 day |  |  | 0% | bar: PERIODS 4
2.2.2 Software Requirements(List soft reqs) |  | 1 day |  |  | 0% | bar: PERIODS 5
2.2.3 Use Case Diagram(form UC diag) |  | 4 hours |  |  | 0% | bar: PERIODS 6
2.2.4 Use Cases(develop use case) |  | 1 day |  |  | 0% | bar: PERIODS 6 to PERIODS 7
2.3 Software Design and System Components |  | 10 days |  |  | 0% | bar: PERIODS 7 to PERIODS 17; PERIODS 19
2.3.1 Software Design |  | 1 day |  |  | 0% | bar: PERIODS 7
2.3.2 System Components |  | 9 days |  |  | 0% | bar: PERIODS 8 to PERIODS 17; PERIODS 19
2.3.2.1 Functions(List Funcs) |  | 2 days |  |  | 0% | bar: PERIODS 8 to PERIODS 9; PERIODS 11
2.3.2.2 Data Structures(Specify data strctures) |  | 2 days |  |  | 0% | bar: PERIODS 9 to PERIODS 10
2.3.2.3 Detailed design(make dtailed design) |  | 5 days |  |  | 0% | bar: PERIODS 8 to PERIODS 12
2.4 User Interface Design |  | 5 days |  |  | 0% | bar: PERIODS 8 to PERIODS 12
2.4.1 Structural Design (specify system env) |  | 1 day |  |  | 0% | bar: PERIODS 8
2.4.2 Visual Design(formulate design elems) |  | 4 days |  |  | 0% | bar: PERIODS 8 to PERIODS 11
3 Software Implementation |  | 13 days |  |  | 0% | bar: PERIODS 17 to PERIODS 29
3.1 Design Implementation |  | 3 days |  |  | 0% | bar: PERIODS 17 to PERIODS 19
3.1.1 Build the User Interface |  | 3 days |  |  | 0% | bar: PERIODS 17 to PERIODS 19
3.1.2 Place the Buttons |  | 10 days |  |  | 0% | bar: PERIODS 19 to PERIODS 28
3.1.3 Add the Colours |  | 4 days |  |  | 0% | bar: PERIODS 20 to PERIODS 24
3.1.4 Build the Layout |  | 3 days |  |  | 0% | bar: PERIODS 20 to PERIODS 22
3.1.4 Build the Logo |  | 3 days |  |  | 0% | bar: PERIODS 20
3.2 Code Construction |  | 3 days |  |  | 0% | bar: PERIODS 21 to PERIODS 24
3.2.1 Coding: Matplotlib |  |  |  |  | 0%
3.2.2 Coding: wxPython |  | 5 days |  |  | 0% | bar: PERIODS 20 to PERIODS 25
3.2.3 Coding: Pandas |  | ???? |  |  | 0% | bar: PERIODS 21 to PERIODS 25
3.3 Design Integration |  | 7 days |  |  | 0% | bar: PERIODS 20 to PERIODS 28
3.3.1 Coding: Landing Page |  |  |  |  | 0% | bar: PERIODS 20 to PERIODS 26
3.3.2 Coding: Suburn Listing Page |  | 3 days |  |  | 0% | bar: PERIODS 20 to PERIODS 32
3.3.3 Coding: Price Chart Page |  | 1hr |  |  | 0% | bar: PERIODS 20 to PERIODS 32
3.3.4 Coding: Search Page |  |  |  |  | 0% | bar: PERIODS 2 to PERIODS 32
3.3.5 Coding: Cleanliness Page |  |  |  |  | 0%
3.3.6 Coding: Display by Ratings Page |  |  |  |  | 0%
4 Software Testing Report
4.1 Document Test Cases
4.2 Build Test Data based on test Cases
4.3 Perform user acceptance testing procedures
4.4 Perform user acceptance testing procedures
4.5 Perform user acceptance testing procedures
5 Executive Summary
5.1 Analysis and Comments(Analys and comments about the software )
5.2 Git_log(Produce Git log report)
Project Completion