## Project Planner
dont know yet
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Project Plan |  | 1 week |  |  | 0 | bar: PERIODS 1 to PERIODS 7
1.1 Project Overview (develop project overview) |  | 1 day |  |  | 0% | bar: PERIODS 1
1.2 Work Breakdown Structure(formulate wbs) |  | 2 days |  |  | 0% | bar: PERIODS 1 to PERIODS 2; PERIODS 5; PERIODS 7
1.3 Activity Definition and Estimation(state activity) |  | 2 days |  |  | 0% | bar: PERIODS 1 to PERIODS 2; PERIODS 7
1.4 Gantt Chart(derive gantt chart from wbs) |  | 2 days |  |  | 0% | bar: PERIODS 2 to PERIODS 3; PERIODS 5; PERIODS 7
2. Software Design Document |  | 19 days? |  |  | 0% | bar: PERIODS 4 to PERIODS 22
2.1 System Vision Statement |  | 6 hours |  |  | 0% | bar: PERIODS 4
2.1.1 Background (explain the bckgrnd) |  | 2 hours |  |  | 0% | bar: PERIODS 4
2.1.2 Overview(give overview of doc) |  | 2 hours |  |  | 0% | bar: PERIODS 4
2.1.3 Benefits(Benefits of the Softwre) |  | 2 hours |  |  | 0% | bar: PERIODS 4
2.2 Requirements |  | 3 days |  |  | 0% | bar: PERIODS 4 to PERIODS 7
2.2.1 User Requirements(List user reqs) |  | 1 day |  |  | 0% | bar: PERIODS 4
2.2.2 Software Requirements(List soft reqs) |  | 1 day |  |  | 0% | bar: PERIODS 5
2.2.3 Use Case Diagram(form UC diag) |  | 4 hours |  |  | 0% | bar: PERIODS 6
2.2.4 Use Cases(develop use case) |  | 1 day |  |  | 0% | bar: PERIODS 6 to PERIODS 7
2.3 Software Design and System Components |  | 10 days |  |  | 0% | bar: PERIODS 7 to PERIODS 17; PERIODS 19
2.3.1 Software Design |  | 1 day |  |  | 0% | bar: PERIODS 7
2.3.2 System Components |  | 9 days |  |  | 0% | bar: PERIODS 8 to PERIODS 17; PERIODS 19
2.3.2.1 Functions(List Funcs) |  | 2 days |  |  | 0% | bar: PERIODS 8 to PERIODS 9; PERIODS 11
2.3.2.2 Data Structures(Specify data strctures) |  | 2 days |  |  | 0% | bar: PERIODS 9 to PERIODS 10
2.3.2.3 Detailed design(make dtailed design) |  | 5 days |  |  | 0% | bar: PERIODS 8 to PERIODS 12
2.4 User Interface Design |  | 5 days |  |  | 0% | bar: PERIODS 8 to PERIODS 12
2.4.1 Structural Design (specify system env) |  | 1 day |  |  | 0% | bar: PERIODS 8
2.4.2 Visual Design(formulate design elems) |  | 4 days |  |  | 0% | bar: PERIODS 8 to PERIODS 11
3 Software Implementation |  | 13 days |  |  | 0% | bar: PERIODS 17 to PERIODS 29
3.1 Design Implementation |  | 3 days |  |  | 0% | bar: PERIODS 17 to PERIODS 19
3.1.1 UI Design(storyboard? ) |  | 3 days |  |  | 0% | bar: PERIODS 17 to PERIODS 19
3.2 Code Construction |  | 10 days |  |  | 0% | bar: PERIODS 19 to PERIODS 28
3.2.1 Landing Page Code(code the Landing page) |  | 4 days |  |  | 0% | bar: PERIODS 20 to PERIODS 24
3.2.2 Matplotlib Code(code the) |  | 3 days |  |  | 0% | bar: PERIODS 20 to PERIODS 22
3.2.3 Tkinter Code/wxPython(1day only)(build layout) |  | 3 days |  |  | 0% | bar: PERIODS 20
3.2.4 Pandas Code(code the) |  | 3 days |  |  | 0% | bar: PERIODS 21 to PERIODS 24
4 Software Testing Report |  |  |  |  | 0%
4.1 Testing Plan(formulate unit tests) |  | 5 days |  |  | 0% | bar: PERIODS 20 to PERIODS 25
4.2 Ongoing testing(Ongoing Testing) |  | ???? |  |  | 0% | bar: PERIODS 21 to PERIODS 25
4.3 User Manual(Create user MAnual) |  | 7 days |  |  | 0% | bar: PERIODS 20 to PERIODS 28
5 Executive Summary |  |  |  |  | 0% | bar: PERIODS 20 to PERIODS 26
5.1 Analysis and Comments(Analys and comments about the software ) |  | 3 days |  |  | 0% | bar: PERIODS 20 to PERIODS 32
5.2 Git_log(Produce Git log report) |  | 1hr |  |  | 0% | bar: PERIODS 20 to PERIODS 32
0% | bar: PERIODS 2 to PERIODS 32
Project Completion |  |  |  |  | 0%
0%